## 2024
StreamWatch Database Project Plan
PROJECT TITLE | [5 empty] | COMPANY NAME | [6 empty] | The Watershed Institute | [15 empty] | KEY |  | Planned |  |  |  | Overtime
PROJECT MANAGERS | [5 empty] | DATE | [6 empty] | 2024-08-28 | [17 empty] | Completed
TASK NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | % OF TASK COMPLETE | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  |  |  | February |  |  |  |  | March |  |  |  |  | April |  |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
[6 empty] | Wk1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Database Plan
1.1 | Intro & Orientation | 2024-08-25 | 2024-09-30 | 35 | 61.11% | bar: September Wk1 to September 5
1.1 a | Basic intro to relational databases | 2024-08-25 | 2024-09-15 | 20 | 50% | bar: September Wk1 to September 2
1.1 b | Tour of current progress | 2024-09-15 | 2024-09-25 | 10 | 83.33% | bar: September 3 to September 4
1.1 c | Figure out how to work collaboratively in database | 2024-09-25 | 2024-09-30 | 5 | 50% | bar: September 5
1.2 | Import Legacy Data | 2024-10-01 | 2024-12-31 | 90 | 12.5% | bar: October 1 to December 5
1.2 a | Finalize methods data | 2024-01-01 | 2024-10-31 | 300 | 50% | bar: October 1 to October 5
1.2 b | Split data & add methods keys | 2024-10-01 | 2024-10-31 | 30 | 0% | bar: October 3 to November 5
1.2 c | Create/Update results table | 2024-10-01 | 2024-10-15 | 14 | 0% | bar: October 1 to October 3
1.2 d | Import and organize data in new database | 2024-11-01 | 2024-12-31 | 60 | 0% | bar: November 1 to December 5
1.3 | Volunteer Tracking |  |  | 0 | 23.12%
1.3 a | Import volunteers from Donor Perfect |  |  | 0 | 0%
1.3 b | Update volunteer assignments |  |  | 0 | 48.33%
1.3 c | Update volunteer training data |  |  | 0 | 19.17%
1.3 d | Plan volunteer onboarding workflow |  |  | 0 | 25%
1.4 | Visit Tracking |  |  | 0 | 8.333%
1.4 a | Import existing visit data |  |  | 0 | 0%
1.4 b | Link volunteers to visits |  |  | 0 | 0%
1.5 | Site Tracking |  |  | 0 | 0%
1.5 a | Import site info & history |  |  | 0 | 0%
1.5 b | Link sites to assignments |  |  | 0 | 0%
1.5 c | Link sites to visits |  |  | 0 | 0%
1.6 | Flag/Error Tracking |  |  | 0 | 0%
1.6 a | Create flag list |  |  | 0 | 0%
1.6 b | Create flag table |  |  | 0 | 0%
1.6 c | Create related fields in other tables |  |  | 0 | 0%
1.6 d | Add flag fields to forms |  |  | 0 | 0%
1.7 | Create import/export workflows |  |  | 0 | 0%
1.7 a | Export & map volunteer addresses |  |  | 0 | 0%
1.7 b | Export & map site priorities |  |  | 0 | 0%
1.7 c | Import & map BACT data |  |  | 0 | 0%
1.7 d | Export volunteer updates to DP |  |  | 0 | 0%
1.8 | Create Data Entry & Analysis Workflows |  |  | 0 | 0%
1.8 a | Finalize CAT data entry methods |  |  | 0 | 0%
1.8 b | Finalize BACT data entry methods |  |  | 0 | 0%
1.8 c | Finalize BAT data entry methods |  |  | 0 | 0%
1.8 d | Finalize BACT analysis workflow |  |  | 0 | 0%
1.8 e | Finalize Report Card analysis workflow |  |  | 0 | 0%
1.8 f | Create user guide/manual |  |  | 0
1.9 | Track ideas for future improvements |  |  | 0 | 0%
1.1 | Intro & Orientation
1.1 a | Basic intro to relational databases |  |  | 0 | 50% | bar: September Wk1 to September 2
| Verbal intro to the concept of relational databases | 2024-08-25 | 2024-08-25 | 0 | 100%
| Read Access 2019 Bible intro |  |  | 0 | 0%
1.1 b | Tour of current progress |  |  | 0 | 83.33% | bar: September 3 to September 4
| Show existing tables & relationships |  |  | 0 | 100%
| Show existing forms, queries and reports |  |  | 0 | 100%
| Review project goals |  |  | 0 | 50%
1.1 c | Figure out how to work collaboratively in database |  |  | 0 | 50% | bar: September 5
| Review Sharepoint sharing options |  |  | 0 | 100%
| Review cloud-based sharing options w/in Access |  |  | 0 | 0%
1.2 | Import Legacy Data
1.2 a | Finalize methods data |  |  | 0 | 50%
| Review WQX methods formats |  |  | 0 | 75%
| Finalize chemical methods |  |  | 0 | 50%
| Finalize meter methods |  |  | 0 | 25%
| Finalize bacterial methods |  |  | 0 | 75%
| Finalize biological methods |  |  | 0 | 75%
| Export methods keys |  |  | 0 | 0%
1.2 b | Split data & add methods keys |  |  | 0 | 0%
| CAT - Create visit codes and separate out visit & habitat data |  |  | 0 | 0%
| CAT - Attach method key for each parameter |  |  | 0 | 0%
| BACT - Create visit codes and separate out visit & habitat data |  |  | 0 | 0%
| BACT - Attach method key for each parameter |  |  | 0 | 0%
| BAT - Create visit codes and separate out visit & habitat data |  |  | 0 | 0%
| BAT - Attach method key for each parameter |  |  | 0 | 0%
1.2 c | Create/Update results table |  |  | 0 | 0%
| Merge all CAT, BAT & BACT results fields (not visit or habitat) |  |  | 0 | 0%
| Add methods key field for each parameter |  |  | 0 | 0%
| Add flag key field for each parameter (or just yes/no indicator) |  |  | 0 | 0%
1.2 d | Import and organize data in new database |  |  | 0 | 0%
| Import visit data |  |  | 0 | 0%
| Import results data |  |  | 0 | 0%
| Import bacterial data |  |  | 0 | 0%
| Import habitat data |  |  | 0 | 0%
1.3 | Volunteer Tracking in Access
1.3 a | Import volunteers from Donor Perfect |  |  | 0 | 0%
| Export Donor Perfect StreamWatch data |  |  | 0 | 0%
| Update with current StreamWatch volunteer data |  |  | 0 | 0%
| Reformat and import volunteer data to new database |  |  | 0 | 0%
1.3 b | Update volunteer assignments |  |  | 0 | 48.33%
| Finalize assignment table schema |  |  | 0 | 90%
| Export & format assignment data for import |  |  | 0 | 75%
| Create & run query for assignment import |  |  | 0 | 50%
| Create assignments forms |  |  | 0 | 75%
| Check & update assignment data |  |  | 0 | 0%
| Create assignment reports |  |  | 0 | 0%
1.3 c | Update volunteer training data |  |  | 0 | 19.17%
| Finalize training table schema |  |  | 0 | 90%
| Export & format training data for import |  |  | 0 | 25%
| Create & run query for training import |  |  | 0 | 0%
| Create training forms |  |  | 0 | 0%
| Check & update training data |  |  | 0 | 0%
| Create training reports |  |  | 0 | 0%
1.3 d | Plan volunteer onboarding workflow |  |  | 0 | 25%
1.4 | Visit Tracking in Access
1.4 a | Import existing visit data |  |  | 0 | 8.333%
| Finalize visit table schema |  |  | 0 | 50%
| Collect & format visit data for import |  |  | 0 | 0%
| Create & run query for visit import |  |  | 0 | 0%
| Finalize visit forms & flows |  |  | 0 | 0%
| Check & update visit data |  |  | 0 | 0%
| Create visit reports |  |  | 0 | 0%
1.4 b | Link volunteers to visits |  |  | 0 | 0%
1.5 | Site Tracking
1.5 a | Import site info & history |  |  | 0 | 0%
| Update sites w/ new groundtruthing info |  |  | 0 | 0%
| Review and update site codes |  |  | 0 | 0%
1.5 b | Link sites to assignments |  |  | 0 | 0%
| Add site keys to assignments table |  |  | 0 | 0%
1.5 c | Link sites to visits |  |  | 0 | 0%
| Add site keys to visit table |  |  | 0 | 0%
1.6 | Flag/Error Tracking
1.6 a | Create flag list |  |  | 0 | 0%
| List common errors in visit data |  |  | 0 | 0%
| List common errors in chemical data |  |  | 0 | 0%
| List common errors in bacterial data |  |  | 0 | 0%
| List common errors in biological data |  |  | 0 | 0%
| List common flags for training/QA/QC/accreditation |  |  | 0 | 0%
1.6 b | Create flag table |  |  | 0 | 0%
| Create table for recording flags |  |  | 0 | 0%
| Create relationships between flags table & other relavant tables |  |  | 0 | 0%
| Finalize table schema |  |  | 0 | 0%
1.6 c | Create related fields in other tables |  |  | 0 | 0%
| Decide how to link flag records to volunteer records |  |  | 0 | 0%
| Decide how to link flag records to site records |  |  | 0 | 0%
| Decide how to link flag records to visit records |  |  | 0 | 0%
| Decide how to link flag records to data records |  |  | 0 | 0%
| Decide how to link flag records to training records |  |  | 0 | 0%
1.6 d | Add flags fields to forms |  |  | 0 | 0%
1.7 | Create import/export workflows
1.7 a | Export & map volunteer addresses |  |  | 0 | 0%
| Decide on format for upload to AGO |  |  | 0 | 0%
| Create export process in Access |  |  | 0 | 0%
| Create overwritable base layers in AGO (CAT, BAT & BACT) |  |  | 0 | 0%
1.7 b | Export & map site priorities |  |  | 0 | 0%
| Decide on format for upload to AGO |  |  | 0 | 0%
| Create export process in Access |  |  | 0 | 0%
| Create overwritable base layers in AGO (CAT, BAT & BACT) |  |  | 0 | 0%
1.7 c | Import & map BACT data |  |  | 0 | 0%
| Decide on how to merge BACT spreadhseets w/ new database |  |  | 0 | 0%
| Create import/export process in Access |  |  | 0 | 0%
1.7 a | Export volunteer updates to DP |  |  | 0 | 0%
1.8 | Create Data Entry & Analysis Workflows
1.8 a | Finalize CAT data entry methods |  |  | 0 | 0%
| Finalize Gallery data import methods |  |  | 0 | 0%
| Finalize Hanna meter log data import methods |  |  | 0 | 0%
| Complete & lock data entry forms |  |  | 0 | 0%
| Verify data connections are working properly |  |  | 0 | 0%
| Complete & lock data view forms |  |  | 0 | 0%
1.8 b | Finalize BACT data entry methods |  |  | 0 | 0%
| Finalize Survey123 data import methods |  |  | 0 | 0%
| Finalize Gallery data import methods |  |  | 0 | 0%
| Complete & lock data entry forms |  |  | 0 | 0%
| Verify data connections are working properly |  |  | 0 | 0%
| Complete & lock data view forms |  |  | 0 | 0%
1.8 c | Finalize BAT data entry methods |  |  | 0 | 0%
| Complete & lock bug count entry forms |  |  | 0 | 0%
| Complete & lock data entry forms |  |  | 0 | 0%
| Verify data connections are working properly |  |  | 0 | 0%
| Complete & lock data view forms |  |  | 0 | 0%
1.8 d | Finalize BACT analysis workflow |  |  | 0 | 0%
| Write queries/scripts to generate parameter scores & averages |  |  | 0 | 0%
| Format export for AGO Dashboard |  |  | 0 | 0%
1.8 e | Finalize Report Card analysis workflow |  |  | 0 | 0%
| Write queries/scripts to generate site counts, scores & averages |  |  | 0 | 0%
| Write queries/scripts to generate regional counts & scores |  |  | 0 | 0%
| Write queries/scripts to export for upload to AGO |  |  | 0 | 0%
1.8 f | Create user guide/manual |  |  | 0 | 0%
| Write general description of database purpose and function |  |  | 0 | 0%
| Describe data entry and analysis workflow |  |  | 0 | 0%
| Describe reports |  |  | 0 | 0%